## Team A
CONSTRUCTION SITE OF THE FUTURE
Human-Robot Collaboration Design Challenge
TEAM A DECISION SHEET
Team Name
Architecture Lead
Robot Engineer
Cost Manager
PROJECT SCENARIO
Your team has been hired to plan material delivery operations for a new high-rise office building. Construction materials must move from a temporary storage area to multiple work zones. The client wants the work completed quickly, safely, and within budget. Because of labour shortages and interest in automation, your team may combine human workers and construction robots.
PROJECT REQUIREMENTS
Requirement | Value
Project Duration | 5 Days
Total Materials | 100 Material Loads
Required Capacity | 20 Loads / Day
Budget Limit | 200 Credits
TEAM ROLES
Role | Focus | Discussion Lens
Architecture Lead | Worker wellbeing; safe site operation; practical implementation | Can this work safely on a real site?
Robot Engineer | Automation; productivity; technical performance | How can robots improve throughput?
Cost Manager | Budget control; resource efficiency | Is the solution affordable and efficient?
AVAILABLE RESOURCES
Human Resources | Cost | Capacity | Support Rule
Construction Material Worker | 10 | 1 Load / Day | Manual material transport worker; adds 1 load/day.
Robot Support Worker | 10 | 0 Loads / Day | Supports robot operations; does not add direct transport capacity.
Robot Resources | Cost | Capacity | Human Support Requirement
Delivery Robot | 20 | 3 Loads / Day | 0.5 support workers per Delivery Robot
Quadruped Robot | 35 | 5 Loads / Day | 1 support worker per Quadruped Robot
Multi-Robot Fleet | 60 | 8 Loads / Day | 3 support workers per Multi-Robot Fleet
ROUND 1 - COST-DRIVEN DESIGN
Client Objective: deliver the project at the lowest possible cost. Select resources, then check whether the solution is feasible.
Resource Selection | Quantity | Notes |  |  | Dashboard Results | Auto-Calculated
Construction Material Workers |  | Manual transport capacity |  |  | Dashboard Results | 0
Robot Support Workers |  | Dedicated support for robot operation |  |  | Required Robot Support Workers | 0
Delivery Robots |  | 0.5 support workers per robot |  |  | Support Worker Check | Status
Quadruped Robots |  | 1 support worker per robot |  |  | Capacity Check | Status
Multi-Robot Fleets |  | 3 support workers per fleet |  |  | Total Cost | 0
Site Resource Visual |  |  |  |  | Estimated Project Duration
[5 empty] | Schedule Status | Status
Round 1 Team Discussion |  |  |  |  | Capacity Target Achievement
Round 1 Winner Rule | Lowest-cost feasible solution wins.
ROUND 2 - TARGET VALUE DESIGN
The client has revised the project priorities. Cost remains important, but the client also wants improved Productivity, Operational Safety, and Manual Physical Effort Reduction. Your goal is to pass all Round 2 constraints and maximize the strategy-weighted Final Value Score. Robot type affects strategy-weighted Final Value Scores. Selected HRC Strategy only changes scoring weights; it does not directly add or subtract points.
Step 1 - Select HRC Strategy |  | Robot-Led | Collaborative | Human-Led | Scoring Lens | Rule
Productivity |  | 40% | 30% | 30% | Final Value Score | Weighted by selected HRC Strategy
Operational Safety |  | 30% | 40% | 30%
Manual Effort Reduction |  | 30% | 30% | 40%
Selected Strategy |  |  |  |  | Winner | Highest strategy-weighted score among eligible teams; lower cost breaks ties; strategy alignment is feedback only
Step 2 - Resource Selection | Quantity | Notes | Productivity | Operational Safety | Manual Effort Reduction | Auto Cost | Step 3/4 - Auto Performance and Eligibility | Auto Value
Construction Material Workers |  | Manual transport capacity | 0 | 0 | 0 | 0
Robot Support Workers |  | Dedicated support for robot operation | 0 | 0 | 0 | 0 | Net Daily Capacity | 0
Delivery Robots |  | 0.5 support workers per robot | 5 | 5 | 8 | 0 | Required Robot Support Workers | 0
Quadruped Robots |  | 1 support worker per robot | 10 | 10 | 12 | 0 | Support Worker Check | Status
Multi-Robot Fleets |  | 3 support workers per fleet | 18 | 8 | 18 | 0 | Capacity Check | Status
Total | [6 empty] | Total Cost | 0
Productivity
Operational Safety
Manual Physical Effort Reduction
Final Value Score
Estimated Completion Time
Site Resource Visual | [6 empty] | Capacity Target Achievement
Robot Resource Share
Robot Capacity Share
Actual Operational Mode
Strategy–Operation Alignment
Round 2 Constraint Verification
[7 empty] | Target Requirement | Actual Value | Target | Status
[7 empty] | Capacity |  | >= 20 loads/day
WINNER DETERMINATION | [6 empty] | Budget |  | <= 200
Round | Winner Rule | [5 empty] | Productivity |  | >= 70
Round 1 | Lowest-cost feasible solution wins. | [5 empty] | Operational Safety |  | >= 70
Round 2 | Highest strategy-weighted Final Value Score among eligible teams wins. | [5 empty] | Manual Physical Effort Reduction |  | >= 70
Tie-breaker | If tied in Round 2, the lower-cost eligible solution wins.
Strategy–Operation Alignment Penalty
Final Team Recommendation (one sentence)
Final Team Recommendation (one sentence)
Facilitator note: yellow cells are editable inputs. Blue dashboard cells calculate automatically. The Scoring Backend sheet contains editable costs, capacities, value weights, constraints, and the 50 / 50 / 50 baseline scoring assumption.

## Scoring Backend
SCORING BACKEND - Editable Workshop Parameters
Resource | Cost | Daily Capacity | Resource Note |  | HUMAN SUPPORT REQUIREMENTS | Support Coefficient | Participant Meaning
Construction Material Worker | 10 | 1 | Manual material transport worker. Directly produces transport capacity. |  | Support Requirement per Delivery Robot | 0.5 | 0.5 Robot Support Workers per Delivery Robot
Robot Support Worker | 10 | 0 | Supports robot operation only; does not add manual transport capacity. |  | Support Requirement per Quadruped Robot | 1 | 1 Robot Support Worker per Quadruped Robot
Delivery Robot | 20 | 3 | Robot transport capacity. |  | Support Requirement per Multi-Robot Fleet | 3 | 3 Robot Support Workers per Multi-Robot Fleet
Quadruped Robot | 35 | 5 | Robot transport capacity.
Multi-Robot Fleet | 60 | 8 | Fleet transport capacity.
HRC Strategy Weights |  |  |  |  | Robot Type | Cost / Unit | Productivity Effect | Safety Effect | Manual Effort Effect
Performance Criteria | Human-Led | Collaborative | Robot-Led | Note | Delivery Robot | 20 | 5 | 5 | 8
Productivity | 40% | 30% | 30% | Selected strategy changes weighting only | Quadruped Robot | 35 | 10 | 10 | 12
Operational Safety | 30% | 40% | 30% | No direct strategy bonus/penalty | Multi-Robot Fleet | 60 | 18 | 8 | 18
Manual Effort Reduction | 30% | 30% | 40% | Robot choices create performance effects
Project Parameter | Value |  |  |  | Value Constraint | Value | Metric | Weight | Higher Means
Project Duration (Days) | 5 |  |  |  | Budget Limit | 200 | Productivity | 0.3 | Faster / more efficient task execution
Total Materials (Material Loads) | 100 |  |  |  | Minimum Operational Safety | 70 | Operational Safety | 0.4 | Lower accident or hazardous-event likelihood
Required Capacity (Loads / Day) | 20 |  |  |  | Minimum Productivity | 70 | Manual Physical Effort Reduction | 0.3 | Less lifting, carrying, fatigue, and strain
Budget Limit (Credits) | 200 |  |  |  | Minimum Manual Physical Effort Reduction | 70
Base Productivity Score | 50 |  |  |  | Human-Led Guidance Share | 35% | Robot Capacity Share < 35%
Base Operational Safety Score | 50 |  |  |  | Collaborative Min Share | 35% | Robot Capacity Share >= 35%
Base Manual Physical Effort Reduction Score | 50 |  |  |  | Collaborative Max Share | 75% | Robot Capacity Share <= 75%
[5 empty] | Robot-Led Guidance Share | 75% | Robot Capacity Share > 75%
[5 empty] | Alignment Penalty | 10 | Deducted from Final Value Score when Selected Strategy and Actual Operational Mode are misaligned
SCORING NOTE
SCORING NOTE: Team sheets use two worker pools. Construction Material Workers directly create manual transport capacity. Robot Support Workers are reserved for robot operation and only satisfy robot support requirements; they do not create manual transport capacity. Total capacity = material-worker capacity + robot capacity. Required Robot Support Workers = 0.5 × Delivery Robots + 1 × Quadruped Robots + 3 × Multi-Robot Fleets. Support check = Robot Support Workers >= Required Robot Support Workers.

## Team B
CONSTRUCTION SITE OF THE FUTURE
Human-Robot Collaboration Design Challenge
TEAM B DECISION SHEET
Team Name
Architecture Lead
Robot Engineer
Cost Manager
PROJECT SCENARIO
Your team has been hired to plan material delivery operations for a new high-rise office building. Construction materials must move from a temporary storage area to multiple work zones. The client wants the work completed quickly, safely, and within budget. Because of labour shortages and interest in automation, your team may combine human workers and construction robots.
PROJECT REQUIREMENTS
Requirement | Value
Project Duration | 5 Days
Total Materials | 100 Material Loads
Required Capacity | 20 Loads / Day
Budget Limit | 200 Credits
TEAM ROLES
Role | Focus | Discussion Lens
Architecture Lead | Worker wellbeing; safe site operation; practical implementation | Can this work safely on a real site?
Robot Engineer | Automation; productivity; technical performance | How can robots improve throughput?
Cost Manager | Budget control; resource efficiency | Is the solution affordable and efficient?
AVAILABLE RESOURCES
Human Resources | Cost | Capacity | Support Rule
Construction Material Worker | 10 | 1 Load / Day | Manual material transport worker; adds 1 load/day.
Robot Support Worker | 10 | 0 Loads / Day | Supports robot operations; does not add direct transport capacity.
Robot Resources | Cost | Capacity | Human Support Requirement
Delivery Robot | 20 | 3 Loads / Day | 0.5 support workers per Delivery Robot
Quadruped Robot | 35 | 5 Loads / Day | 1 support worker per Quadruped Robot
Multi-Robot Fleet | 60 | 8 Loads / Day | 3 support workers per Multi-Robot Fleet
ROUND 1 - COST-DRIVEN DESIGN
Client Objective: deliver the project at the lowest possible cost. Select resources, then check whether the solution is feasible.
Resource Selection | Quantity | Notes |  |  | Dashboard Results | Auto-Calculated
Construction Material Workers |  | Manual transport capacity |  |  | Dashboard Results | 0
Robot Support Workers |  | Dedicated support for robot operation |  |  | Required Robot Support Workers | 0
Delivery Robots |  | 0.5 support workers per robot |  |  | Support Worker Check | Status
Quadruped Robots |  | 1 support worker per robot |  |  | Capacity Check | Status
Multi-Robot Fleets |  | 3 support workers per fleet |  |  | Total Cost | 0
Site Resource Visual |  |  |  |  | Estimated Project Duration
[5 empty] | Schedule Status | Status
Round 1 Team Discussion |  |  |  |  | Capacity Target Achievement
Round 1 Winner Rule | Lowest-cost feasible solution wins.
ROUND 2 - TARGET VALUE DESIGN
The client has revised the project priorities. Cost remains important, but the client also wants improved Productivity, Operational Safety, and Manual Physical Effort Reduction. Your goal is to pass all Round 2 constraints and maximize the strategy-weighted Final Value Score. Robot type affects strategy-weighted Final Value Scores. Selected HRC Strategy only changes scoring weights; it does not directly add or subtract points.
Step 1 - Select HRC Strategy | Cost | Human-Led | Collaborative | Robot-Led | Scoring Lens | Rule
Productivity | Human-Led | 40% | 30% | 30% | Final Value Score | Weighted by selected HRC Strategy
Operational Safety | 40% | 30% | 40% | 30%
Manual Effort Reduction | 30% | 30% | 30% | 40%
Selected Strategy |  |  |  |  | Winner | Highest strategy-weighted score among eligible teams; lower cost breaks ties; strategy alignment is feedback only
Step 2 - Resource Selection | Quantity | Notes | Productivity | Operational Safety | Manual Effort Reduction | Auto Cost | Step 3/4 - Auto Performance and Eligibility | Auto Value
Construction Material Workers |  | Manual transport capacity | 0 | 0 | 0 | 0
Robot Support Workers |  | Dedicated support for robot operation | 0 | 0 | 0 | 0 | Net Daily Capacity | 0
Delivery Robots |  | 0.5 support workers per robot | 5 | 5 | 8 | 0 | Required Robot Support Workers | 0
Quadruped Robots |  | 1 support worker per robot | 10 | 10 | 12 | 0 | Support Worker Check | Status
Multi-Robot Fleets |  | 3 support workers per fleet | 18 | 8 | 18 | 0 | Capacity Check | Status
Total | [6 empty] | Total Cost | 0
Productivity
Operational Safety
Manual Physical Effort Reduction
Final Value Score
Estimated Completion Time
Site Resource Visual | [6 empty] | Capacity Target Achievement
Robot Resource Share
Robot Capacity Share
Actual Operational Mode
Strategy–Operation Alignment
Round 2 Constraint Verification
[7 empty] | Target Requirement | Actual Value | Target | Status
[7 empty] | Capacity |  | >= 20 loads/day
WINNER DETERMINATION | [6 empty] | Budget |  | <= 200
Round | Winner Rule | [5 empty] | Productivity |  | >= 70
Round 1 | Lowest-cost feasible solution wins. | [5 empty] | Operational Safety |  | >= 70
Round 2 | Highest strategy-weighted Final Value Score among eligible teams wins. | [5 empty] | Manual Physical Effort Reduction |  | >= 70
Tie-breaker | If tied in Round 2, the lower-cost eligible solution wins.
Strategy–Operation Alignment Penalty
Final Team Recommendation (one sentence)
Final Team Recommendation (one sentence)
Facilitator note: yellow cells are editable inputs. Blue dashboard cells calculate automatically. The Scoring Backend sheet contains editable costs, capacities, value weights, constraints, and the 50 / 50 / 50 baseline scoring assumption.

## Team C
CONSTRUCTION SITE OF THE FUTURE
Human-Robot Collaboration Design Challenge
TEAM C DECISION SHEET
Team Name
Architecture Lead
Robot Engineer
Cost Manager
PROJECT SCENARIO
Your team has been hired to plan material delivery operations for a new high-rise office building. Construction materials must move from a temporary storage area to multiple work zones. The client wants the work completed quickly, safely, and within budget. Because of labour shortages and interest in automation, your team may combine human workers and construction robots.
PROJECT REQUIREMENTS
Requirement | Value
Project Duration | 5 Days
Total Materials | 100 Material Loads
Required Capacity | 20 Loads / Day
Budget Limit | 200 Credits
TEAM ROLES
Role | Focus | Discussion Lens
Architecture Lead | Worker wellbeing; safe site operation; practical implementation | Can this work safely on a real site?
Robot Engineer | Automation; productivity; technical performance | How can robots improve throughput?
Cost Manager | Budget control; resource efficiency | Is the solution affordable and efficient?
AVAILABLE RESOURCES
Human Resources | Cost | Capacity | Support Rule
Construction Material Worker | 10 | 1 Load / Day | Manual material transport worker; adds 1 load/day.
Robot Support Worker | 10 | 0 Loads / Day | Supports robot operations; does not add direct transport capacity.
Robot Resources | Cost | Capacity | Human Support Requirement
Delivery Robot | 20 | 3 Loads / Day | 0.5 support workers per Delivery Robot
Quadruped Robot | 35 | 5 Loads / Day | 1 support worker per Quadruped Robot
Multi-Robot Fleet | 60 | 8 Loads / Day | 3 support workers per Multi-Robot Fleet
ROUND 1 - COST-DRIVEN DESIGN
Client Objective: deliver the project at the lowest possible cost. Select resources, then check whether the solution is feasible.
Resource Selection | Quantity | Notes |  |  | Dashboard Results | Auto-Calculated
Construction Material Workers |  | Manual transport capacity |  |  | Dashboard Results | 0
Robot Support Workers |  | Dedicated support for robot operation |  |  | Required Robot Support Workers | 0
Delivery Robots |  | 0.5 support workers per robot |  |  | Support Worker Check | Status
Quadruped Robots |  | 1 support worker per robot |  |  | Capacity Check | Status
Multi-Robot Fleets |  | 3 support workers per fleet |  |  | Total Cost | 0
Site Resource Visual |  |  |  |  | Estimated Project Duration
[5 empty] | Schedule Status | Status
Round 1 Team Discussion |  |  |  |  | Capacity Target Achievement
Round 1 Winner Rule | Lowest-cost feasible solution wins.
ROUND 2 - TARGET VALUE DESIGN
The client has revised the project priorities. Cost remains important, but the client also wants improved Productivity, Operational Safety, and Manual Physical Effort Reduction. Your goal is to pass all Round 2 constraints and maximize the strategy-weighted Final Value Score. Robot type affects strategy-weighted Final Value Scores. Selected HRC Strategy only changes scoring weights; it does not directly add or subtract points.
Step 1 - Select HRC Strategy | Cost | Human-Led | Collaborative | Robot-Led | Scoring Lens | Rule
Productivity | Human-Led | 40% | 30% | 30% | Final Value Score | Weighted by selected HRC Strategy
Operational Safety | 40% | 30% | 40% | 30%
Manual Effort Reduction | 30% | 30% | 30% | 40%
Selected Strategy |  |  |  |  | Winner | Highest strategy-weighted score among eligible teams; lower cost breaks ties; strategy alignment is feedback only
Step 2 - Resource Selection | Quantity | Notes | Productivity | Operational Safety | Manual Effort Reduction | Auto Cost | Step 3/4 - Auto Performance and Eligibility | Auto Value
Construction Material Workers |  | Manual transport capacity | 0 | 0 | 0 | 0
Robot Support Workers |  | Dedicated support for robot operation | 0 | 0 | 0 | 0 | Net Daily Capacity | 0
Delivery Robots |  | 0.5 support workers per robot | 5 | 5 | 8 | 0 | Required Robot Support Workers | 0
Quadruped Robots |  | 1 support worker per robot | 10 | 10 | 12 | 0 | Support Worker Check | Status
Multi-Robot Fleets |  | 3 support workers per fleet | 18 | 8 | 18 | 0 | Capacity Check | Status
Total | [6 empty] | Total Cost | 0
Productivity
Operational Safety
Manual Physical Effort Reduction
Final Value Score
Estimated Completion Time
Site Resource Visual | [6 empty] | Capacity Target Achievement
Robot Resource Share
Robot Capacity Share
Actual Operational Mode
Strategy–Operation Alignment
Round 2 Constraint Verification
[7 empty] | Target Requirement | Actual Value | Target | Status
[7 empty] | Capacity |  | >= 20 loads/day
WINNER DETERMINATION | [6 empty] | Budget |  | <= 200
Round | Winner Rule | [5 empty] | Productivity |  | >= 70
Round 1 | Lowest-cost feasible solution wins. | [5 empty] | Operational Safety |  | >= 70
Round 2 | Highest strategy-weighted Final Value Score among eligible teams wins. | [5 empty] | Manual Physical Effort Reduction |  | >= 70
Tie-breaker | If tied in Round 2, the lower-cost eligible solution wins.
Strategy–Operation Alignment Penalty
Final Team Recommendation (one sentence)
Final Team Recommendation (one sentence)
Facilitator note: yellow cells are editable inputs. Blue dashboard cells calculate automatically. The Scoring Backend sheet contains editable costs, capacities, value weights, constraints, and the 50 / 50 / 50 baseline scoring assumption.

## Summary
WORKSHOP SUMMARY - TEAM COMPARISON
This dashboard compares Team A, Team B, and Team C. The game now separates worker allocation into Construction Material Workers and Robot Support Workers. Construction Material Workers create manual transport capacity; Robot Support Workers only support robots. Round 1 rewards the lowest-cost capacity-and-support feasible solution. Round 2 uses target value design: teams must pass core constraints first. Robot type affects Final Value Scores, while Selected HRC Strategy changes the weights used in Final Value Score.
Winner Dashboard | Result
Round 1 Winner | No feasible team yet
Round 2 Winner | No eligible team
Round 2 Tie-Breaker | Highest penalty-adjusted Final Value Score among eligible teams, then lowest cost
Round 1 Comparison | Net Daily Capacity | Support Worker Check | Capacity Check | Budget Check | Total Cost | Feasible? | Winner Score
Team A | 0 | Status | Status | Status | 0 | Status
Team B | 0 | Status | Status | Status | 0 | Status
Team C | 0 | Status | Status | Status | 0 | Status
Round 2 Comparison | Selected Strategy | Robot Resource Share | Robot Capacity Share | Actual Operational Mode | Strategy–Operation Alignment | Net Daily Capacity | Support Worker Check | Capacity Check | Total Cost | Productivity | Operational Safety | Manual Physical Effort Reduction | Penalty-Adjusted Final Value Score | Eligible? | Tie-Break Score | Winner?
Team A | [5 empty] | 0 | Status | Status | 0 |  |  |  |  | Status
Team B | [5 empty] | 0 | Status | Status | 0 |  |  |  |  | Status
Team C | [5 empty] | 0 | Status | Status | 0 |  |  |  |  | Status
Chart Team | Penalty-Adjusted Final Value Score
Team A
Team B
Team C
0

## Formula Tests
Test | Expected logic | Formula / Link | Status | Notes
Round 1 capacity | material workers + robot capacity | 0 | Check after input | B45 material, B46 support, B47:B49 robots
Round 1 support | support workers >= robot support load | Status | Check after input | B46 compared with G46
Round 2 capacity | material workers + robot capacity | 0 | Check after input | B73 material, B74 support, B75:B77 robots
Round 2 support | support workers >= robot support load | Status | Check after input | B74 compared with J75
Team recommendation section | Only final one-sentence recommendation remains | Team sheets A99 only | OK